Focus: The EW Conference

Marketing and Operations Plans 2023

# Goals:

SALES GOALS:

120 paid attendees

- 2019: 127 paid attendees

- 2020: 160 registered attendees, 83 different companies

- 2022: 106 registered attendees

25 booths sold, $60,000 in sponsorships

- 2019: 23 paid, 10 VGM – 33 total

- 2020: 25 vendors, 31 including VGM

- 2022: 29 vendors, including 4 VGM

- Goal: $60,000 in sponsorships and attendee participation fees

Ruth Addison Award: 20 Nominees

- 2021: 11 Nominees

- 2022: 13 Nominees

MARKETING OBJECTIVES

Key targets: Leadership, billing & reimbursement/operations, compression, mastectomy, mother/baby

Marketing Goals:

- Create leads for follow-up calls to be made by Outbound Communications and EW Team

- Generate awareness of Focus Conference and Ruth Addison Award

- Increased web traffic on focus.essentiallywomen.com

- Registrations

# Targeted Audiences:

GROUPS TO TARGET:

- EW Members – All members

  - Secondary audience: VGM only with mastectomy purchases to encourage participation and EW membership

    - Are you interested in building your women’s health business?

    - Put in Connect – want to boost your women’s health business? Attend Focus

      - Oct-Jan: Event Calendar

      - Oct-Nov: Post about Focus and why they should attend

- Vendors

  - Contracted with EW

  - Contracted with VGM

  - Select non-participating

# Dates

Feb. 3-4: Pre-conference

- ABC Class

Feb 4 (1-4 p.m.): Pre-Conference

- Billing & Reimbursement 101 Course with Ronda Buhrmester (intake, best practices, billing codes, modifiers, clearing houses, submitting claims)

- Lunch is not included

Feb. 4-6, 2023 at the Sheraton Sand Key Resort, Clearwater Beach, FL

Feb. 4: American Breast Care Reception from 6-9 in Beach/Gulf Room at the resort

- Attendees only

- No specific RSVP from EW, but include on our website

- Marketing comms to tell people what to expect

# Pricing

- Full Conference Registration: $275 per person

- On-Site Registration: $350

- Billing & Reimbursement Pre-Con: $50

- On-Site Billing & Reimbursement Pre-Con: $75

- Tradeshow Only: $100

# Special Offers

- Early Bird (Sept. 26-Nov. 30): $225 per person

- Early Bird Buy 4 Get 1 Free (Sept. 26-Nov. 30) $180 per person

- Buy 4 Get 1 Free (Dec. 1-Jan. 20) $220 per person

- Early Bird New Member BOGO $112.50 per person

  - Offered to new EW members Feb. 1. 2022 to Jan. 20, 2023

- New Member BOGO $137.50

  - Offered to new EW members Feb. 1. 2022 to Jan. 20, 2023

# Hotel Information

Sheraton Sand Key Resort

1160 Gulf Blvd, Clearwater Beach, FL 33767

Rate: $239

Cutoff for reservations – On or before Jan. 10, 2023 (real date is Jan. 12)

Rate is available Feb. 1 – Feb. 11

Hotel Reservation Link:

Registration Opens: 9/26/22

# Rooms Utilized:

- Palm/Bay/Island II: Exhibit Hall

- Beach/Gulf: General Session, ABC Reception and Dinner

- Bay/Island II: Preconference Friday and Saturday

- Conch Room on 6th Floor for meeting space

- Coastal Room: Office

- VGM to coordinate ABC Pre-conference and reception/dinner

# Marketing Tactics

- Email

  - EW and VGM members who do mastectomy (ABC Purchasers)

- Personal Email

- Email Signature

- Calls – from EW

- Calls – Outbound Communications

- Websites: essentiallywomen.com and focus.essentiallywomen.com

- VGM Website – Event VGM

- VGM Connect – Event and October Blog

- Social Media Posts– 1 per month beginning October

  - Feature a presenter or topic each month

- Facebook Event

- Mailed Prospectus – October

- Newsletter – Each Month beginning September

- eProspectus (digital version) - November

- Postcard – first week of Jan

- Blogs – 1 per month beginning October

  - Feature a presenter or topic each month

- Buckslips with quarterly statements – Q3 and Q4

# Messaging & Positioning:

Focus Conference will be positioned as:

- The best show for education, networking and hospitality

- Major benefit of membership

- Place for members to recharge and gain valuable knowledge to do business better

- Premier education

  - Two Keynotes

  - Earn CEUs, scientific and business

  - More scientific sessions (once approved)

- Exhibitors, exhibit hall

  - An innovative show – see the latest technology

  - See what’s new and take advantage of show specials

- New this year:

  - Pre-conference session with Ronda

  - Cocktail reception for Exhibit Hall Grand Opening on Sunday evening

  - Topics include mastectomy, billing & reimbursement, menopause and breast cancer, patient perspectives and best practices

- Pricing breaks

  - Early Bird Full Conference Registration: $225 per person

  - Early Bird with Billing & Reimbursement Pre-con: $275

  - Full Conference Registration: $275 per person

  - Registration with Billing & Reimbursement: $350

  - On-Site Registration: $350

  - On-Site with Billing & Reimbursement: $425

  - Tradeshow Only: $100

  - Buy 4 get 1 free

- Attendee Comms:

  - Flip flop party? Remind of temps, don’t wear heels on the beach

  - Program or email to include recommended restaurants

# Implementation/Frequency:

- Press release

  - Late September: Registration Open and Speakers Announced

  - October: Nominations for Ruth Addison Award Open

  - November: Finalists for RA Award

  - December: Keynotes Announced

  - February: RA Award Winner

- EW Calling Campaigns: Ongoing topic Sept through Feb.

- Buck Slip – Q3 (mid-Sept) and Q4 (mid-Nov)

- Flyer: One – to be distributed by EW, ABC, VGM Insurance, VGM RAMs and MAMs - October

- Mailed Prospectus and eProspectus: November

- OBC Calling Campaigns: Early November and Early January

- Email campaign

  - Sept 27– Save the Date

  - Late Sept – Registration Open

  - Sept 27 – Dec 31: Emails on first and third Tuesday (8 emails)

    - Sept 27, Oct 4, Oct 18, Nov 1, Nov 15, Nov 29, Dec 6, Dec 20

    - Sept-Feb RA Award

  - Jan: Emails on 1st, 2nd, and 3rd Tuesdays (3 emails)

    - Jan 3, Jan 10, Jan 17 (last chance)

- Social

  - Sept through Dec: 2nd and 4th weeks of each month

  - January through Conference: Weekly

  - Facebook Event

    - Sept through Dec: 1 post on the event page per month

    - January: post details as needed, goal: two posts in January

- Discussion Board - Monthly

- Blog – Monthly in EW Newsletter beginning Oct.

- Hero/Banner Ad on EW Website, Focus website – Sept-Feb

- Email Signature – Sept-Oct: Register Now early bird registration, Nov-Feb: Register Now, Book your room before room block is full

- Events Calendar on vgm.com – Sept-Feb

- Connect Events Calendar in VGM Connect

# Other Marketing/Collateral Needs

Focus Conference PowerPoint (Sept for Oct distribution)

Exhibitor/Sponsorship Packet/Flier

Focus Conference Program

Nametags

Signage

VGM Staff shirts for party

Focus Conference Staff apparel

# Focus Education

Focus 2023 Education Steps

- Create a list of potential speakers (July/August)

- Create Microsoft Form to gather speaker submissions (August)

- Solicit applications to speak (August)

- Select speakers and sessions (August/September)

- Confirm speakers and determine date and time of each session (August/September)

- Obtain photos, bios, session learning objectives, overview paragraph (August/September)

- Provide presentation background (October)

- Submit Conference for CEUs (October)

- Assist with developing room monitor schedule (Nov)

- Main contact for Keynotes (Dec, Jan)

- Communicate Focus Details (Nov, Dec, Jan, Feb)

- Obtain final presentations and handouts (December/January)

- Arrange presentation needs (December/January)

- Place session PowerPoint files on session laptops (Feb at Show)

- Responsible for A/V in education sessions

# Exhibitors and Sponsors

Steps to secure exhibitors and sponsors for Focus 2023

- Determine pricing, sponsorship opportunities (Sept)

- Prepare tradeshow rules and regs packet (Sept)

- Determine vendors to invite (Sept)

- Determine how vendors will register and collect payment (Sept)

- Solicit and select exhibitors and sponsors (Sept - Dec)

- Determine layout of the show floor and assign booths (Oct - Dec)

- Notify exhibitors and provide exhibit house info (Nov - Dec)

- Double check info from exhibitors for program (Dec/Jan)

- Obtain list of booth staff for nametags (Dec/Jan)

- SALE OF BOOTH SPACE AND SPONSORS MUST END 12/15/22 DUE TO MARKETING DEADLINES

- Vendor payments due 12/31/22

# Operations Activity:

September 2022

- Create a list of potential speakers

- Create a form to gather speaker applications

- Discussion Board Post

- Invite speakers

- Review speaker submissions

- Select speakers and sessions

- Obtain speaker collateral

- Determine vendors to invite

- Build and Open Vendor Sponsorship

- Create Attendee registration

- Build and Finalize Schedule

- Review speaker submissions

- Select and confirm speakers and sessions

- Obtain speaker collateral

- Provide presentation background to speakers

- Build and Open Vendor Sponsorship and Exhibitor registration

- Build and Finalize Attendee Registration

- Solicit Exhibitors and Sponsors

- Opportunities: Create in CRM

- EW Community Calls begin

  - New Members since 2/1/22

  - Past Attendees 2019-2022

  - Top Tier

October 2022

- Finalize schedule

- Submit Conference for CEUs

- Solicit vendors for exhibiting and sponsoring

- Calls

- Discussion Board Post

November 2022

- Solicit exhibitors and sponsors

- Finalize Exhibitors and Sponsors, shut down registration

- Notify Exhibitors and Sponsors of deadlines for commercials, any collateral need for buyers guide or sample box

- Calls

- Discussion Board Post

December 2022

- Any sample box items due 12/31/20

- Gather and confirm information for Buyer’s Guide is in

- Calls

- Discussion Board Post

January 2023

- Continue calls

- Prep Focus meeting materials

  - Note Sheets

  - Attendee lists

  - Create room monitor schedules and host trainings

February 2023

- Handwritten thank you notes to speakers, exhibitors and attendees

- Submit conference to ABCOP/BOC week of March 7

# Marketing Activity by Month (BASIC)

## September 2022

Sept 14: Save the Date Mention in Newsletter

Sept 14: Save the Date Social Post

Sept 14: Discussion board Save the Date

Sept 27: Email 1 Registration Open

Sept 27: Registration Open Social Post

Sept 27: Registration Open Press Release

Prep Ruth Addison Award Timeline (separate document)

Prep Exhibitor/Sponsorship Packet/Flier

Enter job for updated Focus PPT Background

Update Focus Website

Prepare tradeshow rules and regs packet

Prep Flier for Sales Use, in-hands End of Sept

Update Speaker Schedule on Website

October 2022:

Oct 4: Email 2

Oct 12: Newsletter - Blog

Week of Oct 17: Social

Oct 18: Email 3

Oct 20: Discussion Board

Oct 27: Important Updates

Prep OBC Script

Prospectus email and mailed

Connect submission

November 2022

Early November: OBC Campaign

Nov 1: Email 4

Week of Nov 8: Social 5

Nov 9: Newsletter - Blog

Nov 15: Email 5

Nov 17: Discussion board

Week of Nov 21: Social

Nov 20: Email 6

December 2022:

Dec 6: Email 7

Week of Dec 12: Social

Dec 14: Newsletter

Dec 20: Email 8

Dec 22: Discussion Board

Week of Dec 27: Social

Prep all signage

Nametags

January 2023:

SHIP DATE: JAN 6

Early January: OBC Campaign

Jan 3: Email 9

Week of Jan 2: Social 8

Jan 10: Email 10

Jan 11: Newsletter

Week of Jan 11: Social

Jan 17: Email 11 – Last Chance

Jan 17: Discussion Board

Week of Jan 16: Social

Jan 30: Know before you go attendee email

Week of Jan 31: Social

February 2023:

Feb 2: Welcome to Focus

Feb 7: Thank You Email to Exhibitors and Attendees with Survey

Feb 8: EW Newsletter